## Ресурсы
Название | Тип | Единицы измерения материалов | Краткое название | Группа | Макс. единиц | Стандартная ставка | Ставка сверхурочных | Затраты на использование | Начисление | Базовый календарь | Заметки
Project manager | Трудовой |  | PM | PMO | 100 | 4300 | 8600 | 0 | Пропорциональное | Стандартный | Coordinates project tasks and schedules and ensures that the project is completed on time and within budget
BI solution architect | Трудовой |  | A | BI team | 100 | 4900 | 9800 | 0 | Пропорциональное | Стандартный | Has overall responsibility for the technical design of the data warehousing solution
System analyst | Трудовой |  | SA | BI team | 100 | 3200 | 6400 | 0 | Пропорциональное | Стандартный | Examines and understands the data-related requirements, objectives, and constraints of the organization to design and develop an effective BI system
MSSQL developer | Трудовой |  | MD | BI team | 100 | 4400 | 8800 | 0 | Пропорциональное | Стандартный | Builds database and ETL workflows to meet business requirements in analysis and reporting
Report developer | Трудовой |  | RD | BI team | 100 | 4400 | 8800 | 0 | Пропорциональное | Стандартный | Creates the reporting elements of the BI solution
DevOps specialist | Трудовой |  | DO | BI team | 100 | 4400 | 8800 | 0 | Пропорциональное | Стандартный | Implements the server and network infrastructure for the data warehousing solution, deploys solution in production environment, setting up CI/CD pipelines
Database administrator | Трудовой |  | DBA |  | 100 | 0 | 0 | 0 | Пропорциональное | Стандартный | Maintains data warehouse, provides access for users
Business users | Трудовой |  | BU |  | 100 | 0 | 0 | 0 | Пропорциональное | Стандартный | Provide requirements and help to prioritize the business questions that the data warehousing solution will answer. Often, the team includes a business analyst as a full-time member to help interpret the business questions and ensure that the solution desi
Testers | Трудовой |  | T | BI team | 100 | 3200 | 6400 | 0 | Пропорциональное | Стандартный | Verify the business and operational functionality of the solution as it is developed

## Назначения
Название задачи | Название ресурса | Трудозатраты | Единицы
Project planning | BI solution architect | 8 | 100
Project planning | Project manager | 8 | 100
Business requirements definition | System analyst | 200 | 100
Business requirements definition | BI solution architect | 100 | 100
Technical architecture design | System analyst | 10 | 100
Technical architecture design | BI solution architect | 40 | 100
Planning software | DevOps specialist | 16 | 100
Planning software | BI solution architect | 16 | 100
Dimensional modelling | System analyst | 40 | 100
Dimensional modelling | MSSQL developer | 40 | 100
BI application design | Report developer | 40 | 100
Physical design | MSSQL developer | 20 | 100
Physical design | DevOps specialist | 20 | 100
ETL design | MSSQL developer | 80 | 100
Resources & software installation | DevOps specialist | 40 | 100
ETL development | MSSQL developer | 160 | 100
BI application development | Report developer | 160 | 100
Deployment | BI solution architect | 40 | 100
Deployment | DevOps specialist | 40 | 100
Testing | Testers | 80 | 100
RELEASE 1 | BI solution architect | 0 | 100

## Задачи
Режим задачи | Название | Длительность | Предшественники | Предварительная оценка | Уровень структуры
Автоматическое планирование | Planning, analyze, design |  |  | Да | 1
Автоматическое планирование | Project planning | 1 |  | Да | 2
Автоматическое планирование | Business requirements definition | 22 | 2 | Да | 2
Автоматическое планирование | Technical architecture design | 3 | 3 | Да | 2
Автоматическое планирование | Planning software | 1 | 4 | Да | 2
Автоматическое планирование | Dimensional modelling | 33 | 3 | Да | 2
Автоматическое планирование | BI application design | 5 | 3 | Да | 2
Автоматическое планирование | Physical design | 3 | 6 | Да | 2
Автоматическое планирование | ETL design | 10 | 8 | Да | 2
Автоматическое планирование | Development |  |  | Да | 1
Автоматическое планирование | Resources & software installation | 4 | 5 | Да | 2
Автоматическое планирование | ETL development | 40 | 9 | Да | 2
Автоматическое планирование | BI application development | 40 | 7 | Да | 2
Автоматическое планирование | Deployment | 5 | 10 | Да | 1
Автоматическое планирование | Testing | 10 | 14 | Да | 1
Автоматическое планирование | RELEASE 1 | 0 | 15 | Да | 1